Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

Reaunch Preparation Cover Letter

Preparation for a relaunch workshop involves the following steps.

- Check that all of the needed materials are on hand.  The materials you need are as follows

- Relaunch Checklist (Checklist PREPR or PREPRm)

- Workshop Schedule (Workshop Schedule or TSPm Workshop Schedule)

- Team Member Relaunch Preparation Package

- Team Leader Relaunch Preparation Package

- Other Member Relaunch Preparation Package

- Launch Notebooks

- Tell the TSP coach that you have received the workshop materials.

- The TSP launch notebooks should be on hand, but they are not needed until the opening day of the relaunch workshop.

- Follow TSP/TSPm Relaunch Preparation Checklist PREPR/PREPRm for a relaunch.

- Make sure that all attendees are available for the workshop during the times specified on the checklist.

- Make sure that all observers know they are only to attend the opening workshop meeting.  There are no observers for workshop meetings 2 through 7.

- Distribute the appropriate preparation materials to the relaunch workshop attendees at least a week before the start of the workshop.

- Team Leader:  Relaunch Preparation Package Team Leader

- Team Member:  Relaunch Preparation Package Team Members

- Other participant:  Relaunch Preparation Package Other Attendee

- Make sure that the meeting facilities and catering are arranged.

- Inform the TSP coach that you are prepared for the workshop.

TSP Relaunch Preparation Checklist - PREPR

| Purpose |  | Use this checklist to guide relaunch preparation activities |  |
| --- | --- | --- | --- |
| Weeks Prior to Launch | Step | Description | Completed |
| 6 | Project Identified | The TSP project has been launched and is ready for relaunch. |  |
| 6 | Person Responsible Identified | A person has been named as responsible for relaunch preparation for the project. |  |
| 4 | Team Ready | The team members and team leader are identified and available for the entire relaunch period. |  |
| 4 | Postmortem Scheduled | All team members and the team leader are scheduled to complete a Postmortem (script PM), for the current Launch/Phase, prior to the relaunch. |  |
| 2 | Relaunch Preparation Package Distributed | All team members have received, reviewed, and distributed the relaunch preparation package(s). |  |
| 2 | Team Member Training Done | - All new software engineers have completed PSP training. - All other new members have completed team member training. |  |
| 2 | Management Training Done | - The team leader has completed TSP or PSP management training. - All involved managers and executives have completed TSP or PSP management training. |  |
| 2 | Attendance Confirmed | All relaunch participants know the attendance guidelines and are scheduled to attend. - The TSP team, management, marketing, and other interested parties attend relaunch meeting 1. - Team members attend meetings 2 through 7, and the relaunch PM, with no observers. |  |
| 2 | Schedule Finalized | - All team members and the team leader are committed to attend relaunch meetings 1 through 7 and the relaunch postmortem. |  |
| 1 | Launch Notebooks Distributed | The launch notebooks have been distributed to all team members and the team leader. |  |
| 1 | Team Preparation Package Distributed | The team leader and all of the team's engineers have been given the team and team leader workshop preparation packages, respectively. |  |
| 1 | Other Attendee Preparation Package Distributed | Any other attendees have been given the other attendee workshop preparation package. |  |

(continued on next page)

TSP Relaunch Preparation Checklist - PREPR (continued)

| Weeks Prior to Launch | Step | Description | Completed |
| --- | --- | --- | --- |
| 1 | Meeting 1 Facilities Confirmed | - The room for relaunch meeting 1 is large enough to hold all team members, management representatives, TSP coach(es), and observers. - A projector and screen are available. - The room is available for the morning of day 1. |  |
| 1 | Facilities for Meetings 2 through 7 and Launch Postmortem Confirmed | - For days 1, 2, and 3 (if needed), the following facilities are available. - a conference room with desk-size working space for each team member, the team leader, and TSP coaches - one or more personal computers with the Microsoft Office - two flip-chart easels and a whiteboard with pads and markers - a PC-compatible projector |  |
| 1 | Catering Confirmed (optional) | For days 1, 2, and 3 (if needed), the following are planned. - refreshments at start and for a mid-morning break - soft drinks for a mid-afternoon break - working lunch - a working dinner (pizza?) may be needed for day 1 |  |
| 1 | Final Report Completed | The final project report (script PM) for the current launch/phase/cycle, has been completed and filed in the project notebook and a copy has been submitted to the process asset and data repository manager. |  |

TSPm Relaunch Preparation Checklist - PREPRm

| Purpose |  | To guide launch preparation activities |  |
| --- | --- | --- | --- |
| Weeks Prior to Launch | Step | Description | Completed |
| 6 | Project Identified | The TSP project has been launched and is ready for relaunch. |  |
| 6 | Person Responsible | A person has been named as responsible for relaunch preparation for the project. |  |
| 5 | Pre-Relaunch Preparation | - The leadership team has been formed and the lead TSP coach has been identified. - They all have copies of the PREP and PREPW scripts. |  |
| 4 | Team Ready | The team members, team leaders, project manager, and TSP coaches are identified and available for the entire relaunch period. |  |
| 4 | Postmortem Scheduled | All team members and the team leader are scheduled to complete a postmortem (script PM) for the current launch/phase/cycle prior to the relaunch. |  |
| 2 | Relaunch Preparation Package Distributed | The team members have received, and reviewed the relaunch preparation package(s). |  |
| 2 | Team Member Training Done | - All new software engineers have completed PSP training. - All other new members have completed team member training. |  |
| 2 | Management Training Done | - All new team leaders and managers have completed TSP or PSP management training. - All other involved managers and executives have completed TSP management training. |  |
| 2 | Attendance Confirmed | All relaunch participants know the attendance guidelines and are scheduled to attend. - The TSP team, management, marketing, and other interested parties attend relaunch meetings 1 and 9. - The team leader and team members attend meetings 2 through 8, and the relaunch postmortem, with no observers. |  |
| 2 | Schedule Confirmed | - All team members and the team leader are committed to attend relaunch meetings 1 through 9 and the relaunch postmortem, and management and marketing representatives are prepared and available for meetings 1 and 9. |  |
| 2 | Facilities Needed for Meetings 1 and 9 confirmed | - The room for relaunch meetings 1, 1A, and 9 is large enough to hold all the local team members, managers, and observers. - A projector and screen are available. - For distributed teams, all remote locations participate in meetings 1, and 1A via videoconference. - The room is available for the mornings of day 1. |  |

(continued on next page)

TSPm Launch Preparation Checklist - PREPRm (continued)

| Weeks Prior to Launch | Step | Description | Completed |
| --- | --- | --- | --- |
| 2 | Facilities for Meetings 2 through 8 and Launch Postmortem Confirmed | For days 1, 2, 3, and 4 (if needed) the following facilities are available at each team location for each sub-team. - a conference room with desk-size working space for each team member, the team leader, and TSP coaches - one or more personal computers with the Microsoft Office. - two flip-chart easels and a whiteboard with pads and markers - a PC-compatible projector |  |
| 2 | Facilities Needed for Meetings 3A, 5A, 5B, 6A, 6B, and 7A Confirmed | Rooms with the following facilities are needed on each relaunch day at each team location for the leadership and role manager team meetings (1 room on days 1 and 3 and 2 rooms on day 2). - a conference room with desk-size working space for each team member, the team leader, and TSP coaches - one or more personal computers with the Microsoft Office - two flip-chart easels and a whiteboard with pads and markers - a unit for projecting from a PC - for distributed teams, a telephone or videoconference connection to each remote location |  |
| 2 | Team Preparation Package Distributed | The project manager, team leaders, and all team members have been given the team and team leader workshop preparation packages. |  |
| 2 | Catering Confirmed (optional) | For days 1, 2, 3, and 4 (if needed), the following catering is planned. - morning and mid morning break - working lunch - mid-afternoon break - A working dinner may be needed for days 1, 2, or 3. |  |
| 2 | Launch Notebooks Distributed | The TSPm launch and operations notebooks have been distributed to all new team members. |  |
| 1 | Final Report Completed | The final project report (script PM) for the current launch/phase/cycle, has been completed and filed in the project notebook and a copy has been submitted to the process asset and data repository manager |  |

Standard TSP Launch Workshop Schedule

| When |  | ## What | ## Topics and Attendees |
| --- | --- | --- | --- |
| # Day 1 |  |  |  |
| 8:30 | 10:00 | Meeting 1 | TSP and workshop overview Senior management discussion of the business need for the project Marketing discussion of the market need for the product Coach, team members, team leader, senior management |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:15 | Meeting 2 | Team roles and goals Coach, team members, team leader |
| 12:15 | 1:00 | Lunch |  |
| 1:00 | 3:00 | Meeting 2 (continued) | Coach, team members, team leader |
| 3:00 | 3:15 | Break |  |
| 3:15 | 6:45 | Meeting 3 | Strategy, process, and support planning Coach, team members, team leader |
| # Day 2 |  |  |  |
| 8:00 | 8:30 | Meeting 3 (continued) | Coach, team members, team leader |
| 8:30 | 10:00 | Meeting 4 | Overall project plan Coach, team members, team leader |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:15 | Meeting 4 (continued) | Coach, team members, team leader |
| 12:15 | 1:00 | Lunch |  |
| 1:00 | 1:30 | Meeting 4 (continued) | Coach, team members, team leader |
| 1:30 | 2:30 | Meeting 5 | Quality plan Coach, team members, team leader |
| 2:30 | 2:45 | Break |  |
| 2:45 | 5:00 | Meeting 6 | Detailed engineer and team next-phase plans, balanced plan Coach, team members, team leader |
| # Day 3 |  |  |  |
| 8:30 | 10:15 | Meeting 6 (continued) | Coach, team members, team leader |
| 10:15 | 10:30 | Break |  |
| 10:30 | 12:00 | Meeting 7 | Team risk assessment Coach, team members, team leader |
| 12:00 | 1:00 | Lunch |  |
| 1:00 | 2:30 | Meeting 8 | Management meeting planning Coach, team members, team leader |
| 2:30 | 2:45 | Break |  |
| 2:45 | 5:30 | Work period | Management meeting preparation Team members, team leader |
| # Day 4 |  |  |  |
| 8:30 | 10:00 | Meeting 9 | Senior management reviews the launch results Coach, team members, team leader, senior management |
| 10:00 | 10:30 | Break |  |
| 10:30 | 11:30 | Launch postmortem meeting | Launch postmortem Coach, team members, team leader |
| 11:30 | 12:30 | Lunch |  |
| 12:30 | 4:30 | TSP Process Review | Coach and all new team members |

TSP Relaunch Workshop Schedule

| When |  | ## What | ## Topics and Attendees |
| --- | --- | --- | --- |
| # Day 1 |  |  |  |
| 8:30 | 10:00 | Meeting 1 | Workshop overview Team leader review of project status and any changes in business goals Coach, team members, team leader, and other attendees as appropriate |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:15 | Meeting 2 | Team roles and goals Coach, team members, team leader |
| 12:15 | 1:00 | Lunch |  |
| 1:00 | 3:00 | Meeting 2 (continued) | Coach, team members, team leader |
| 3:00 | 3:15 | Break |  |
| 3:15 | 5:00 | Meeting 3 | Strategy, process, and support planning Coach, team members, team leader |
| # Day 2 |  |  |  |
| 8:00 | 10:15 | Meeting 3 (continued) | Coach, team members, team leader |
| 10:15 | 10:30 | Break |  |
| 10:30 | 12:00 | Meeting 4 | Overall project plan Coach, team members, team leader |
| 12:00 | 1:00 | Lunch |  |
| 1:00 | 3:30 | Meeting 4 (continued) | Coach, team members, team leader |
| 3:30 | 3:45 | Break |  |
| 3:45 | 4:45 | Meeting 5 | Quality plan Coach, team members, team leader |
| # Day 3 |  |  |  |
| 8:00 | 10:00 | Meeting 6 | Detailed engineer and team next-phase plans, balanced plan Coach, team members, team leader |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:15 | Meeting 6 (continued) | Coach, team members, team leader |
| 12:15 | 1:00 | Lunch |  |
| 1:00 | 2:30 | Meeting 7 | Team risk assessment Coach, team members, team leader |
| 2:30 | 2:45 | Break |  |
| 2:45 | 3:45 | Launch postmortem meeting | Launch postmortem Coach, team members, team leader |

TSPm Launch Workshop Schedule

| When |  | ## What | ## Topics and Attendees |
| --- | --- | --- | --- |
| # Day 1 |  |  |  |
| 8:30 | 10:00 | Meeting 1 | Full team and senior management meeting TSP and workshop overview Marketing discussion of the needed product Senior management discussion of the business and project goals For distributed teams, remote members participate via videoconference. |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:15 | Meeting 1A | Common team meeting Discussion of overall project strategy and team assignments For distributed teams, remote members participate via telephone or videoconference. |
| 12:15 | 1:00 | Lunch |  |
| 1:00 | 3:00 | Meeting 2 | Sub-team meetings Team goals and roles |
| 3:00 | 3:15 | Break |  |
| 3:15 | 6:15 | Meeting 3 | Sub-team meetings Strategy, process, and support planning |
| 6:15 | 8:15 | Meeting 3A | Leadership meeting - status and issues, select interim lead role managers For distributed teams, remote members participate via telephone or videoconference |
| # Day 2 |  |  |  |
| 8:00 | 10:00 | Meeting 3 (continued) | Coach, team members, team leader |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:15 | Meeting 4 | Sub-team meetings Overall project plan |
| 12:15 | 1:00 | Lunch |  |
| 1:00 | 3:00 | Meeting 4 (continued) | Coach, team members, team leader |
| 3:00 | 3:15 | Break |  |
| 3:15 | 5:30 | Meeting 4 (continued) | Coach, team members, team leader |
| # Day 3 |  |  |  |
| 8:30 | 10:00 | Meeting 4 (continued) | Coach, team members, team leader |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:00 | Meeting 5 | Sub-team meetings Quality plan |
| 12:00 | 1:00 | Lunch |  |
| 1:00 | 3:15 | Meeting 5 (continued) | Coach, team members, team leader |
| 3:15 | 3:30 | Break |  |
| 3:30 | 5:30 | Meetings 5A, 5B, 5C | Leadership meeting - status and issues Planning managers - consolidated team plan Quality managers – quality issues and consolidated quality plan For distributed teams, remote members participate via telephone or videoconference |

(continued)

TSPm Launch Workshop Schedule (continued)

| When |  | ## What | ## Topics and Attendees |
| --- | --- | --- | --- |
| # Day 4 |  |  |  |
| 8:00 | 10:00 | Meeting 6 | Sub-team meetings Detailed team and engineer next-phase plans, balanced plan |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:00 | Meeting 6 (continued) | Coach, team members, team leader |
| 12:00 | 1:00 | Lunch |  |
| 1:00 | 2:00 | Meetings 6A, 6B | Leadership meeting - status and issues Planning managers meeting - balanced next-phase team plan For distributed teams, remote members participate via telephone or videoconference |
| 2:00 | 3:15 | Meeting 7 | Sub-team meetings Team risk assessment |
| 3:15 | 3:30 | Break |  |
| 3:30 | 4:30 | Meeting 7A | Leadership meeting – status and issues Plan for management presentation For distributed teams, remote members participate via telephone or videoconference |
| 4:30 | 6:00 | Meeting 8 | Sub-team meetings Management meeting planning |
| # Day 5 |  |  |  |
| 8:00 | 9:00 | Meeting 8 (continued) | Coach, team members, team leader |
| 9:00 | 10:30 | Meeting 9 | Full team and senior management meeting Leadership team presents launch results to senior management and the entire team For distributed teams, remote members participate via videoconference. |
| 10:30 | 10:45 | Break |  |
| 10:45 | 12:15 | Postmortem meetings | Leadership team postmortem meeting For distributed teams, remote team leaders participate via telephone or videoconference Sub-team postmortem meetings |

TSPm Relaunch Workshop Schedule

| When |  | ## What | ## Topics and Attendees |
| --- | --- | --- | --- |
| # Day 1 |  |  |  |
| 8:30 | 10:00 | Meeting 1A | Common team meeting Discussion of overall project strategy and team assignments For distributed teams, remote members participate via videoconference. |
| 10:00 | 10:15 | Break |  |
| 10:15 | 11:00 | Meeting 2 | Sub-team meetings Team roles and goals |
| 11:00 | 12:15 | Meeting 3 | Sub-team meetings Strategy, process, and support planning |
| 12:15 | 1:00 | Lunch |  |
| 1:00 | 3:00 | Meeting 3 (continued) | Coach, team members, team leader |
| 3:00 | 3:15 | Break |  |
| 3:15 | 5:00 | Meeting 3A | Leadership meeting - status and issues, select interim lead role managers For distributed teams, remote members participate via telephone or videoconference |
| # Day 2 |  |  |  |
| 8:00 | 10:00 | Meeting 4 | Overall project plan Coach, team members, team leader |
| 10:15 | 10:30 | Break |  |
| 10:30 | 12:00 | Meeting 4 (continued) | Coach, team members, team leader |
| 12:00 | 1:00 | Lunch |  |
| 1:00 | 3:00 | Meeting 5 | Quality plan Coach, team members, team leader |
| 3:00 | 3:15 | Break |  |
| 3:15 | 5:00 | Meetings 5A, 5B, 5C | Leadership meeting - status and issues Planning managers - consolidated team plan Quality managers – quality issues and consolidated quality plan For distributed teams, remote members participate via telephone or videoconference |

(continued)

TSPm Relaunch Workshop Schedule (continued)

| When |  | ## What | ## Topics and Attendees |
| --- | --- | --- | --- |
| # Day 3 |  |  |  |
| 8:00 | 10:00 | Meeting 6 | Detailed engineer and team next-phase plans, balanced plan Coach, team members, team leader |
| 10:00 | 10:15 | Break |  |
| 10:15 | 12:15 | Meeting 6 (continued) | Coach, team members, team leader |
| 12:15 | 1:00 | Lunch |  |
| 1:00 | 2:00 | Meetings 6A, 6B | Leadership meeting - status and issues Planning managers meeting - balanced next-phase team plan For distributed teams, remote members participate via telephone or videoconference |
| 2:00 | 3:15 | Meeting 7 | Sub-team meetings Team risk assessment |
| 3:15 | 3:30 | Break |  |
| 3:30 | 4:30 | Meeting 7A | Leadership meeting – status and issues Plan for management presentation For distributed teams, remote members participate via telephone or videoconference |
| 4:30 | 6:00 | Meeting 8 | Sub-team meetings Management meeting planning |
| # Day 4 |  |  |  |
| 8:00 | 9:00 | Meeting 8 (continued) | Coach, team members, team leader |
| 9:00 | 10:15 | Meeting 9 | Full team and senior management meeting Leadership team presents launch results to senior management and the entire team For distributed teams, remote members participate via videoconference. |
| 10:15 | 10:30 | Break |  |
| 10:30 | 12:00 | Postmortem meeting | Sub-team meetings Launch postmortem |

Notional schedule; it can be compressed or extended to meet scope of launch.

Notional schedule; it can be compressed or extended to meet scope of launch.