Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

TSPm Leadership Team Launch Handouts

| Contents | Launch Workshop |
| --- | --- |
| # Page | Element |
| 2 | Meeting Report - Launch Meeting 1 (partially completed) |
| 3 | TSPm Leadership Team Launch - Script LTL |
| 4 | LTL Launch Meeting 1 - Script LTL1 |
| 5 | Meeting Report - Launch Meeting 2 (partially completed) |
| 6 | LTL Launch Meeting 2 - Script LTL2 |
| 7 | Meeting Report - Launch Meeting 3 (partially completed) |
| 8 | LTL Launch Meeting 3 - Script LTL3 |
| 9 | Meeting Report - Launch Meeting 4 (partially completed) |
| 10 | LTL Launch Meeting 4 - Script LTL4 |
| 11 | Meeting Report - Launch Meeting 5 (partially completed) |
| 12 | LTL Launch Meeting 5 - Script LTL5 |
| 13 | Meeting Report – LTL Postmortem Meeting (partially completed) |
| 14 | LTL Launch Postmortem - Script LTLPM |
| 15 | TSP Issue and Risk Tracking Log - Form ITL (blank) |
| 16 | TSP Process Improvement Proposal - Form PIP (blank) |

Meeting Report - LTL Meeting 1

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | LTL Meeting 1: To overview the LTL process and to guide the leadership team |  |  |  |  |  |  |  |
| in deciding how to work as a leadership team |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 20 |  |  |  |  | Launch overview |  |  |  |  | TSP Coach |  |
| 30 |  |  |  |  | Business goals and expectations |  |  |  |  | Senior Manager |  |
| 30 |  |  |  |  | Goal questions |  |  |  |  | Leadership Team |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

| TSPm Leadership Team Launch - Script LTL |  |
| --- | --- |
| Purpose | To guide the leadership team in conducting a launch workshop |
| Entry Criteria | - The leadership team has completed a TSPm team launch. - Senior management is available for LTL meeting 1. - All leadership team members attend meetings 1 through 5 and the postmortem. - For distributed teams, the remote team leaders participate in the entire launch either in person or via telephone or videoconference. - An authorized TSP coach is on hand to lead the launch. |
| General | - Timing - All LTL meetings are held on one day. - To complete the launch in one day, the entire team may have to stay late. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Business Objectives | - Hold launch meeting 1 (script LTL1). - review the launch process and objectives - discuss the team’s goals with senior management |
| 2 | Define the Team Goals | - Hold launch meeting 2 (script LTL2). The leadership team - defines and documents its goals - relates its goals to business goals - defines goal measures |
| 3 | Determine Oversight Strategy | - Hold launch meeting 3 (script LTL3). The leadership team - reviews its quality, productivity, commitment, and improvement objectives - determines the management and team practices required to meet these objectives - considers the ways to motivate these practices - selects a motivational strategy |
| 4 | Allocate Work to Role Manager Teams | - Hold launch meeting 4 (script LTL4). The leadership team - determines the work and data needed to cause and verify the desired behavior - decides how this work should be done - defines the reports and data needed to accomplish the desired oversight - decides which tasks should be done by which role manager team |
| 5 | Define Role Manager Team Goals and Responsibilities | - Hold launch meeting 5 (script LTL5). The leadership team - lists for each role manager team the results to be produced - decides on the needed frequency and timing of these results - decides which leadership team member will be the contact point for each role manager team - assigns that leadership team member responsibility for preparing and presenting the leadership team’s needs at that role manager team launch |
| PM | Launch Postmortem | - Hold the launch postmortem meeting (script LTLPM). - document the launch results - assess the launch process and prepare PIPs |

| # Exit Criteria | - Documented team goals and goal measures - Defined role manager team responsibilities - Leadership team contact designated for each role manager team - All risks and issues have been identified and recorded. - Launch completed and results documented |
| --- | --- |

| TSPm LTL Launch Meeting 1 - Script LTL1 |  |
| --- | --- |
| Purpose | To review the leadership team’s goals and expectations with senior management |
| Entry Criteria | - One or more senior managers are present and prepared. - All participants are present (TSP coach, team leaders, and project manager). - For distributed teams, remote members participate via telephone or videoconference. - Forms: MTG, ITL, PIP - Specification ROLE |
| General | - Meeting 1 takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Launch Overview Meeting Role Assignments | The TSP coach leads the meeting (script MTG). The TSP coach - describes the LTL launch process and the launch products - reviews the meeting roles and assigns a timekeeper and recorder (specification ROLE) - discusses the work to be done in this meeting |
| 2 | Business Goals and Expectations | The senior manager - describes the business goals for the organization and how this project’s performance relates to these goals - discusses the business objectives for improved quality, productivity, and competitive capability - describes management’s process improvement objectives - outlines management’s expectations for this project - answers the team's questions |
| 3 | Goal Questions | The team members should satisfy themselves that they understand the business goals and the senior manager’s expectations. - the reasons for each goal and expectation - how the senior manager will determine if the goals and expectations are met |
| 4 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the project manager |

| Exit Criteria | - Launch meeting 1 activities have been completed. - The leadership team understands senior management’s goals and expectations. - The team's questions have been answered, or actions planned to get the answers. - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The project manager has copies of all meeting products. |
| --- | --- |

Meeting Report - LTL Meeting 2

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | LTL Meeting 2: To review managements goals and define the leadership team’s |  |  |  |  |  |  |  |
| goals |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| ## Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 10 |  |  |  |  | Review management’s stated goals |  |  |  |  | Project Manager |  |
| 30 |  |  |  |  | Identify management’s implied goals |  |  |  |  | Project Manager |  |
| 25 |  |  |  |  | Define the leadership team’s goals |  |  |  |  | Project Manager |  |
| 15 |  |  |  |  | Assign responsibility for goal tracking |  |  |  |  | Project Manager |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

| TSPm LTL Launch Meeting 2 - Script LTL2 |  |
| --- | --- |
| Purpose | To guide the leadership team in setting goals |
| Entry Criteria | - All participants are present (TSP coach, team leaders, and project manager). - For distributed teams, remote members participate via telephone or videoconference. - Forms: GOAL, ITL, MTG, PIP - Specifications ROLE, PLAN, QUAL |
| General | Meeting 2 generally takes 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Review Management's Stated Goals | The project manager leads the team review of the senior manager’s goals to - get agreement on the stated goals - identify one or more measures for each goal - record results on form GOAL. |
| 4 | Implied Goals | - The project manager leads the team in defining the goals that are implied by management's stated goals. - Considerations include team productivity, quality performance, process improvement, customer satisfaction, and competitive capability. |
| 5 | Team Goals | The project manager leads the team in - establishing team goals to meet the manager's stated and implied goals - identifying one or more measures for each team goal - recording results on form GOAL |
| 6 | Goal Tracking | The project manager leads the team in - assigning team-member tracking responsibility for each goal - recording the assignments on form GOAL - establishing a tracking schedule for each goal |
| 7 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the project manager. |

| Exit Criteria | - Launch meeting 2 activities have been completed. - The team goals are documented (form GOAL). - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The project manager has copies of all meeting products. |
| --- | --- |

Meeting Report - LTL Meeting 3

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | LTL Meeting 3: To define the project results required to meet the team’s goals |  |  |  |  |  |  |  |
| and determine the sub-team practices required to produce these results |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| ## Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 10 |  |  |  |  | Review team objectives |  |  |  |  | Project Manager |  |
| 30 |  |  |  |  | Assess current team performance |  |  |  |  | Project Manager |  |
| 25 |  |  |  |  | Select the motivational strategy |  |  |  |  | Project Manager |  |
| 15 |  |  |  |  | Define the verification strategy |  |  |  |  | Project Manager |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

| TSPm LTL Launch Meeting 3 - Script LTL3 |  |
| --- | --- |
| Purpose | To guide the leadership team in defining the strategy it will use in overseeing the project |
| Entry Criteria | - All participants are present (TSP coach, team leaders, and project manager). - For distributed teams, remote members participate via telephone or videoconference. - The documented team goals are available. - Forms: ITL, MTG, PIP and REVIEW checklist - Specification ROLE |
| General | Meeting 3 generally takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Review Objectives | - The project manager leads the team in - defining the project results required to meet the team’s quality, schedule, productivity, and process improvement goals - reviewing the team’s and sub-teams’ plans for meeting its goals - determining the needed team and sub-team actions to meet these goals |
| 4 | Assess Current Team Performance | The project manager leads the team in - discussing the team’s current performance - defining any needed changes - devising ways to obtain the desired results |
| 5 | Select Management Strategy | - The project manager leads the team in - defining the management actions required to obtain the desired results - determining a strategy for implementing these actions |
| 6 | Define Verification Strategy | The project manager leads the team in - defining ways to verify the desired team results (TSP REVIEW checklist) - identifying measures or other indicators of proper performance - defining a strategy for verifying that the sub-teams are following the desired practices |
| 7 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the project manager |

| Exit Criteria | - Launch meeting 3 activities have been completed. - List of products to be produced has been recorded (form SUMS). - Overall and detailed development process steps are documented. - Process plan and support plan are documented (form INV). - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The lead role manager has copies of all meeting products. |
| --- | --- |

Meeting Report - LTL Meeting 4

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | LTL Meeting 4: To guide the leadership team in assigning project oversight and |  |  |  |  |  |  |  |
| support work |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| ## Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 30 |  |  |  |  | Define needed reports and data |  |  |  |  | Project Manager |  |
| 20 |  |  |  |  | Define required work |  |  |  |  | Project Manager |  |
| 15 |  |  |  |  | Make initial task assignments |  |  |  |  | Project Manager |  |
| 25 |  |  |  |  | Assess role manager team workload |  |  |  |  | Project Manager |  |
| 10 |  |  |  |  | Make role manager team assignments |  |  |  |  | Project Manager |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

| TSPm LTL Launch Meeting 4 - Script LTL4 |  |
| --- | --- |
| Purpose | To guide the leadership team in assigning project oversight and support work |
| Entry Criteria | - All participants present (TSP coach, team leaders, and project manager). - For distributed teams, remote members participate via telephone or videoconference. - Forms: ITL, MTG, PIP - Specification ROLE |
| General | Meeting 4 generally takes 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Define Needed Reports and Data | - The project manager leads the team in - defining the data and reports needed to assess team and project performance - deciding how these data and reports should be produced |
| 4 | Define Required Work | - The project manager leads the team in - determining the work needed to implement the selected strategy - deciding which tasks must be done by the team leaders - specifying the tasks to be handled by the role manager teams - defining the tasks to be assigned to other groups |
| 5 | Make Initial Task Assignments | - The project manager leads the team in making the task assignments. - For the role manager tasks, the team makes an initial assignment. - The team determines who should handle the other delegateable tasks. - The team assigns a team leader to arrange for this other work |
| 6 | Assess Role Manager Team Workload | - The project manager leads the team in - reviewing the workload for each role manager team (TSPm Role Manager Team Responsibilities, TSPm Lead Role Manager Responsibilities) - identifying the role manager teams that are overloaded and those that are not adequately utilized - determining the role manager teams that have continuing reporting tasks and those that do not |
| 7 | Make Role Manager Team Assignments | - The project manager leads the team in assigning the workload so that - no role manager team has an excessive workload - every team has at least one continuing reporting responsibility - every team has sufficient cross-team workload to ensure its continued communication and involvement |
| 8 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the lead role manager |

| Exit Criteria | - Launch meeting 4 activities have been completed. - The role manager team workload has been assigned - Other required oversight tasks have been assigned or delegated. - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The project manager has copies of all meeting products. |
| --- | --- |

Meeting Report - LTL Meeting 5

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | LTL Meeting 5: To guide the leadership team in defining the role manager team |  |  |  |  |  |  |  |
| goals and responsibilities |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| ## Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 30 |  |  |  |  | List role manager team tasks |  |  |  |  | Project Manager |  |
| 30 |  |  |  |  | Define needed reports and data |  |  |  |  | Project Manager |  |
| 15 |  |  |  |  | Define any other role manager team goals |  |  |  |  | Project Manager |  |
| 15 |  |  |  |  | Assign leadership team responsibilities |  |  |  |  | Project Manager |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

| TSPm LTL Launch Meeting 5 - Script LTL5 |  |
| --- | --- |
| Purpose | To guide the leadership team in defining the role manager team goals and responsibilities |
| Entry Criteria | - All participants are present (TSP coach, team leaders, and project manager). - For distributed teams, remote members participate via telephone or videoconference. - Forms: ITL, MTG, PIP and REVIEW checklist - Specification ROLE |
| General | Meeting 5 generally takes 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | List Role Tasks | The project manager leads the team in listing the assignments for each role manager team (see TSPm Role Manager Team Responsibilities). |
| 4 | Define Needed Reports and Data | - For each role manager team report or task, the leadership team - describes the information needed (TSP REVIEW Checklist) - specifies any format constraints or requirements - states the required timing or frequency for the reports - describes why the report is needed and how it will be used |
| 5 | Define Other Goals | - For each role manager team, the leadership team also - lists any other role manager responsibilities (quality alerts, risk evaluations, technical exposures) (Role Manager Team Responsibilities) - describes the leadership team’s other expectations for the role manager team (creative input, emerging opportunities, significant customer related issues) |
| 6 | Leadership Team Responsibilities | - For each role manager team, the leadership team - determines the team leader who will be the contact point for that role manager team - assigns that leadership team member the responsibility for preparing and presenting the leadership team’s needs to that role manager team at its team launch (Script RTL) - asks that team leader to periodically review that role manager team’s activities and to bring any problems to the leadership team (Script WEEKLR) |
| 7 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch meeting 5 activities have been completed. - Precise role manager team reporting responsibilities have been defined. - Other role manager team responsibilities have been specified. - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The lead role manger has copies of all meeting products. |
| --- | --- |

Meeting Report - LTL Postmortem Meeting

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | LTL Meeting 5: To guide the leadership team through the launch postmortem |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| ## Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 10 |  |  |  |  | Review the work to be done |  |  |  |  | TSP Coach |  |
| 30 |  |  |  |  | Conduct the postmortem |  |  |  |  | TSP Coach |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

| TSPm LTL Postmortem Meeting - Script LTLPM |  |
| --- | --- |
| Purpose | To guide the leadership team through the launch postmortem |
| Entry Criteria | - All participants are present (TSP coach, team leaders, and project manager). - For distributed teams, remote members participate via telephone or videoconference. - Forms: ITL, MTG, PIP - Specification ROLE |
| General | Timing - The PM meeting generally takes about ½ to 1 hour. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Launch Postmortem | The TSP coach ensures that all required launch data are gathered and recorded. |
| 4 | Prepare PIPs | The TSP coach leads the team through a process evaluation. - identifies launch process problems or inconveniences - suggests process improvements - completes PIPs for these suggestions |
| 5 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees - gives the completed form MTG to the planning manager |

| Exit Criteria | - Launch postmortem activities have been completed. - All risks and issues have been recorded (form ITL). - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The TSP coach and project manger have copies of all meeting products. |
| --- | --- |

TSP Issue and Risk Tracking Log - Form ITL

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |

TSP Process Improvement Proposal - Form PIP

| Name |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |  |
| Project |  | Launch/Phase |  |  |  |

| PIP Number |  |  | Priority |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PIP Title |  |  |  |  |  |  |  |
| Improvement Description |  |  |  |  |  |  |  |
| Briefly describe the improvement you suggest. |  |  |  |  |  |  |  |
| Process Elements Impacted |  |  |  |  |  |  |  |
| If you know them, list the process elements that must be added, changed, or deleted. |  |  |  |  |  |  |  |
| Improvement Benefits (check one) |  |  |  |  |  |  |  |
| Improved Quality _______ Reduced Cycle Time ________ Reduced Risk ________ |  |  |  |  |  |  |  |
| Describe the likely benefits of the suggested change. |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |
| PIP Control No. |  |  |  | Accepted |  |  |  |
| Received |  |  |  | Returned |  |  |  |
| Evaluated |  |  |  | Deferred |  |  |  |
| Effort Involved |  |  |  | Date Done |  |  |  |
| Author Notified |  |  |  |  |  |  |  |
| Reasons |  |  |  |  |  |  |  |