Copyright 2018 Carnegie Mellon University.  All rights reserved.

This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center.

Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense.

NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS.

[Distribution Statement A] This material has been approved for public release and unlimited distribution.  The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.

The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.

The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

Workshop Handouts - Meetings 7 and 7A

| Contents |  |
| --- | --- |
| Page | Element |
| 2 | Meeting Report - Launch Meeting 7 ( partially completed) |
| 3 | TSP Launch Meeting 7 - Script LAU7 |
| 5 | Meeting Report - Launch Meeting 7A ( partially completed) |
| 6 | TSPm Launch Meeting 7A - Script LAU7A |
| 7 | TSP Issue and Risk Tracking Log - Form ITL (blank) |
| 8 | TSP Process Improvement Proposal - Form PIP (blank) |

Note: for meeting 7, the TSP and TSPm launch and relaunch processes are the same.

Meeting Report - Launch Meeting 7

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSP Launch Meeting 7: To conduct a project risk assessment analysis and |  |  |  |  |  |  |  |
| produce a report on each high-priority risk |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  | Agenda and meeting process |  |  |  |  | TSP Coach |  |
| 75 |  |  |  |  | Conduct project risk assessment |  |  |  |  | Team Leader |  |
| 5 |  |  |  |  | Meeting wrap-up and report |  |  |  |  | TSP Coach |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |
| Completed list of risks with evaluations |  |  |  |  |  |  |  |  |  |  |  |
| Assignments for key risks |  |  |  |  |  |  |  |  |  |  |  |

(Use additional form copies if needed.)

| TSP Launch Meeting 7 - Script LAU7 |  |
| --- | --- |
| Purpose | To guide the team through a project risk assessment |
| Entry Criteria | - All participants are present (TSP coach, team members, team leader). - Documented overall and next-phase development plan are available. - Forms: ITL, MTG, PIP |
| General | - A risk is something that may or may not happen. Something that is certain is an issue, not a risk. - Meeting 7 generally takes 1 to 2 hours, depending on project dynamics. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Roles | Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | The TSP coach reviews the work to be done in this meeting and the products to be produced. |
| 3 | Risk Identification | The team leader asks the team to identify risks. - All team members participate in suggesting risks. - Use a brainstorm approach; i.e., do not evaluate risks during this step. - The process continues until no one can think of any more risks. - Record each risk to aid subsequent evaluation by the team. |
|  | Impact Evaluation | For each risk, the team evaluates its likely impact. - Impact is high if the project schedule impact would be high. - Risks may also have medium or low schedule impact. |
|  | Likelihood Evaluation | For each risk, the team judges its likelihood. Likelihood is also measured as high, medium, or low. |
|  | Source | For each risk, the team determines the source of the risk based on the risk categories. - Engineering: Requirements, Design, Code & Unit Test, Integration & Test, or Engineering Specialties - Development Environment: Development Process, Development System, Management Process, Management Methods, or Work Environment - Program Constraints: Resources, Contract, or Program Interfaces |
|  | Assign Risks | For the high and medium priority risks (i.e., high-high, high-medium, medium-high, or medium-medium), the team - assigns a member to track the risk - sets a date by which mitigation action must be taken - documents the risk, responsibility, and flag date on form ITL |
| 4 | Risk Mitigation | For the high and medium priority risks, identify those that are near-term. - Determine an effective mitigation plan. - Recommend actions to reduce or eliminate risk impact. - If multiple mitigation plans are available, determine if the risk warrants a formal evaluation. If it does, then update plans to execute the decision analysis and resolution process (script DAR). |
| 5 | Launch Meeting Documentation | The recorder completes form MTG. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees and gives the completed form MTG to the planning manager |

(continued on next page)

TSP Launch Meeting 7 - Script LAU7 (continued)

| Exit Criteria | - Launch meeting 7 activities have been completed. - All risks and issues are documented (form ITL). - The high-priority risks have mitigation plans. - All process improvement suggestions have been recorded (form PIP). - The meeting report has been completed (form MTG and attachments). - The planning manger has copies of all meeting products. |
| --- | --- |

Meeting Report – TSPm Launch Meeting 7A

| Name |  |  |  |  |  |  |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson |  | TSP Coach |  |  |  | Location |  |  |  |  |  |
| Meeting Date |  |  |  |  |  | Time From: |  |  |  | To: |  |
| Subject/Purpose |  |  |  | TSPm Launch Meeting 7A: The leadership team meets to review |  |  |  |  |  |  |  |
| launch status, review the identified project risks, resolve issues, and plan for the final management meeting. |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |
| Name |  |  |  |  |  |  |  |  |  | Role |  |
| Agenda |  |  |  |  |  |  |  |  |  |  |  |
| ## Times (min.) |  |  |  |  | Topics |  |  |  |  | Discussion Leader |  |
| Plan | Start |  | Stop |  |  |  |  |  |  |  |  |
| 5 |  |  |  |  | Meeting roles and process |  |  |  |  | TSP Coach |  |
| 5 |  |  |  |  | ### Meeting agenda |  |  |  |  | Project Manager |  |
| 15 |  |  |  |  | Review launch status |  |  |  |  | Team Leaders |  |
| 20 |  |  |  |  | Review the identified issues |  |  |  |  | Project Manager |  |
| 20 |  |  |  |  | Plan for the final management meeting |  |  |  |  | Project Manager |  |
| 10 |  |  |  |  | Review open issues |  |  |  |  | Project Manager |  |
| 10 |  |  |  |  | Other items |  |  |  |  | Project Manager |  |
| 5 |  |  |  |  | Launch meeting documentation |  |  |  |  | Project Manager |  |
| Decisions, Actions, and Key Information |  |  |  |  |  |  |  |  |  |  |  |
| What |  |  |  |  |  |  |  | Who |  |  | When |

(Use additional form copies if needed.)

| TSPm Launch Meeting 7A - Script LAU7A |  |
| --- | --- |
| Purpose | - The leadership team meets to - review launch status and to identify and resolve issues - review the sub-team risk assessments - plan for the management meeting |
| Entry Criteria | - The project manager and team leaders participate in launch meeting 7A. - For distributed teams, remote team leaders and coaches participate via telephone or videoconference. - The team risk assessments have been made and are available. - Forms: MTG, ITL |
| General | - Meeting 7A follows immediately after launch meeting 7. - Meeting 7A takes from 1 to 2 hours. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Meeting Role Assignments | - Select the meeting roles (specification ROLE). - The TSP coach leads the meeting (script MTG). - The timekeeper tracks time and keeps the meeting on schedule. - The recorder notes meeting decisions and actions and writes the meeting report (form MTG). |
| 2 | Meeting Overview | - The lead TSP coach reviews the purpose of the meeting and the results to be produced. |
| 3 | Meeting Agenda | - The project manager - reviews the meeting agenda - asks for changes or additions |
| 4 | Status Review | - Each team leader - reviews the status of his or her team launch - summarizes the principal results to date - identifies problems or issues requiring leadership team attention |
| 5 | Risks Review | - The project manager asks the team leaders to - discuss the major risks the teams have identified - decide which if any risks should be tracked at the project level - decide if any risk evaluations should be changed - identify any additional risks that should be tracked - assign responsibilities for tracking any newly identified risks - record any new or changed risks in the project ITL |
| 6 | Planning for the Management Meeting | - The project manager reviews the agenda items for the management meeting. - discusses the material to be covered (specification STATUS) - assigns the preparation work |
| 7 | Other Items | - The project manager leads the discussion of any other agenda topics. |
| 8 | Launch Meeting Documentation | - The recorder gives the completed form MTG to the project manager. - lists the attendees and the time spent by agenda item - describes decisions made and by whom - documents pending actions: what, when, and by whom - verifies the meeting report with the meeting attendees |

| # Exit Criteria | - The status of each team’s launch reviewed. - All risks and issues are documented (form ITL). - Assignments made for preparing the management report presentation. - The meeting report has been completed (form MTG and any attachments). |
| --- | --- |

TSP Issue and Risk Tracking Log - Form ITL

| Name |  | Date |  |
| --- | --- | --- | --- |
| Project |  | Launch/Phase |  |

| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |
| No. | Date |  | Personal/Team | Risk/Issue | Impact | Likelihood | Source | Owner |
| Description |  |  |  |  |  |  |  | Follow-up Date |
|  |  |  |  |  |  |  |  | Resolved Date |

TSP Process Improvement Proposal - Form PIP

| Name |  |  | Date |  |  |
| --- | --- | --- | --- | --- | --- |
| E-mail |  | Organization |  |  |  |
| Project |  | Launch/Phase |  |  |  |

| PIP Number |  |  | Priority |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| PIP Title |  |  |  |  |  |  |  |
| Improvement Description |  |  |  |  |  |  |  |
| Briefly describe the improvement you suggest. |  |  |  |  |  |  |  |
| Process Elements Impacted |  |  |  |  |  |  |  |
| If you know them, list the process elements that must be added, changed, or deleted. |  |  |  |  |  |  |  |
| Improvement Benefits (check one) |  |  |  |  |  |  |  |
| Improved Quality _______ Reduced Cycle Time ________ Reduced Risk ________ |  |  |  |  |  |  |  |
| Describe the likely benefits of the suggested change. |  |  |  |  |  |  |  |
| When completed and reviewed, submit to the Process Manager and keep a copy. |  |  |  |  |  |  |  |
| Do not write below this line. |  |  |  |  |  |  |  |
| PIP Control No. |  |  |  | Accepted |  |  |  |
| Received |  |  |  | Returned |  |  |  |
| Evaluated |  |  |  | Deferred |  |  |  |
| Effort Involved |  |  |  | Date Done |  |  |  |
| Author Notified |  |  |  |  |  |  |  |
| Reasons |  |  |  |  |  |  |  |