## Slide 1: Launching a TSP Project
Software Engineering Institute
Carnegie Mellon University
Pittsburgh, PA 15213
September 2010
Notes: Title Slide
  Title and Subtitle text blocks should not be moved from their position if at all possible.

## Slide 3: Trademarks and Service Marks
The following are service marks of Carnegie Mellon University.
  CMMISM
  Team Software ProcessSM
  TSPSM
  Personal Software ProcessSM
  PSPSM
The following are registered trademarks of Carnegie Mellon University.
  Capability Maturity Model®
  CMM®
  Capability Maturity Model® Integration
  CMMI®
  CERT®
Notes: <number>

## Slide 4: The Software Engineering Institute
The TSP was developed at the Software Engineering Institute (SEI), a unit of Carnegie Mellon University (CMU).
Your agreement with CMU to use the TSP materials requires that you provide data from TSP projects to the SEI.
The SEI will use that data to
  improve the TSP
  provide guidelines and benchmark data to TSP users to help them plan and manage TSP projects
The SEI will not publicize or attribute your data without your explicit permission, unless you have already published these data in a public setting.
Notes: <number>

## Slide 5: Why We are Here
The purpose of this workshop is to launch your project.
This workshop
  performs essential planning tasks that are part of the project work
  is not a course
It is the first step in starting your TSP project.
The purpose for meeting 1 is for
organizational and project management to describe the project objectives and management goals to the team
team members to understand what the team is supposed to do
Notes: <number>

## Slide 6: The Launch Workshop Notebook
In the launch workshop notebook are
  the launch schedule
  handouts for each launch meeting
    handout contents
    meeting agenda and meeting script
    launch scripts and forms
    lecture overheads
  planning, quality, and management briefing guidelines
  role, notebook, status, and summary specifications
  forms, and scripts
Notes: <number>
This slide and the following 3 slides are primarily for first time teams. When launching with a team that has used TSP before, these slides can be skipped.

## Slide 7: The TSP Launch Process
The TSP launch is organized as a set of meetings.
Each TSP meeting has roles, an agenda, and a meeting report.
The meeting roles are
  Chairperson: arranges and leads the meeting
  Facilitator/timekeeper
    helps the team follow the agenda and the script
    tracks and notes meeting times on the agenda
  Recorder
    records all important decisions (what and who) and planned actions (what, who, when)
    verifies the actions and decisions with the meeting attendees at the end of the meeting
Notes: <number>
Note: the meeting process is described on page 4 and the meeting roles are described on page 3 of the meeting 1 section of the Launch notebook
After going through this slide, ask for volunteers to be the timekeeper and recorder for this meeting.

## Slide 8: This Meeting’s Agenda
The TSP launch process
Discussions
  Management: the business need for the project
  Marketing: the desired product
Notes: <number>

## Slide 9: Purpose of the TSP Launch
The launch establishes a common team understanding of the project.
  management’s goals for the project
  team and team members’ goals
  processes that the team will use
  roles that the team members will perform
  development work to be done
  plan for doing the work
  management and customer reporting system
  ongoing team communication process
Notes: <number>

## Slide 10: The Launch Process
1. Establish
product and
Business goals
2. Assign roles
and define
team goals
Build
overall and
near-term plans
5. Develop
the quality
plan
6. Build individual
and consolidated
plans
7. Conduct
risk
assessment
8. Prepare
management
briefing and
launch report
Launch
postmortem
9. Hold
management
review
3. Produce
development
strategy
and process
A TSP coach guides the team
through a defined process to develop
its plan and to negotiate that plan with
management.
Notes: SEI Presentation (Basic)
Author, Date
07/30/26

## Slide 11: Meeting 1: Establishing Product and Business Goals
The first step in the TSP launch is for senior management and a marketing (or a customer) representative to tell the team
  what they want the team to develop
  when the product is needed
  the resources available to the team
  the team’s flexibility
  why the job is important
  how management will measure success
Notes: <number>

## Slide 12: TSP Launch Outcomes -1
Input
  Business needs
  Management goals
  Product requirements
  Trained resources
  Process assets
  Historical data
  TSP Coach
Output
  Quantitative team goals linked to business needs, management goals, and product requirements
  Team role manager assignments for self-directed team and objective evaluation of adherence to plan and process
  List of key features, requirements, and work products
  Cyclic product development strategy
  Size estimate for each work product
Notes: © 2008 Carnegie Mellon University
Presentation Title
07/30/26

## Slide 13: TSP Launch Outcomes -2
Output (continued)
  Tailored process for each work product
  Task plan for each work product based on the tailored process
  Effort estimate for each task
  Estimated schedule of available resources
  Earned value plan
  Milestones for schedule-based product and business objectives
  Quantitative quality plan to meet product and business objectives
Output (continued)
  Quantitative product and process quality criteria for controlling phase entry and exit for each work product
  Risk assessment and mitigation plan
  Assigned resource for every business and product objective, work product, task, goal, and risk
  Overall plan to end of project
  Detailed next-cycle plan
  Alternative plans
  Approved plans
  Empowered and committed team
Notes: © 2008 Carnegie Mellon University
Presentation Title
07/30/26

## Slide 14: This Meeting’s Agenda
The TSP launch process
Discussions
  Management: the business need for the project
  Marketing: the desired product
Notes: <number>

## Slide 15: Management: The business need for the project
Notes: SEI Presentation (Basic)
Author, Date
07/30/26

## Slide 16: Marketing: The desired product
Notes: SEI Presentation (Basic)
Author, Date
07/30/26

## Slide 17: Backup Slides
Notes: SEI Presentation (Basic)
Author, Date
07/30/26

## Slide 18: The Meeting Agenda
Every TSP meeting should have an agenda that
  describes the meeting’s purpose
  lists the attendees
  gives the topics and their planned times
  names the discussion leader
The agenda for this meeting is under the tab “Meeting 1”.
By having an agenda, you will have more productive meetings.
Notes: <number>
The meeting report instructions (on page 5 of the “Meeting 1” tab) describe how to prepare the meeting notice/agenda and complete the decisions, actions, and key information sections of the meeting report.

## Slide 19: The Meeting Report
If a meeting is worth holding, it is worth reporting.
The meeting report should
  be brief
  list the key decisions and conclusions
  record all planned actions
Verifying the actions and decisions will help you to
  agree on what is to be done and remember to do it
  meet your commitments
Notes: <number>

## Slide 20: Meeting 2: Establishing Team Self-direction
The team sets its goals and picks its roles.
The team starts with the goals that management stated in the opening meeting.
  reviews and refines these goals
  adds team-specific goals
  agrees on the team’s goals
The team divides the team management roles so each member has a role responsibility.
Planning Manager | Design Manager
Quality Manager | Test Manager
Process Manager | Customer Interface Manager
Support Manager | Implementation Manager
Notes: <number>

## Slide 21: Meeting 3: Producing the Development Strategy
The team looks at the project from several perspectives.
The team members define the product that they will build and how to build it.
  conceptual design and size estimate
  strategy for meeting the team’s goals
  list of all the products that must be produced
  process for doing the job right the first time
  list of any support activities that must be done by the team
Size estimates help the team to estimate how much time the project will take.
The team describes the strategy and process independent of schedule constraints.
Project strategy
Process, support
List of products
Development strategy
Conceptual
design
Notes: <number>

## Slide 22: Meeting 4: Building the Overall Plan
The team builds an overall plan for the entire job.
Tasks are defined in sequence from project start to finish. They
  follow the team’s process
  include all products
  are detailed for the next phase
The time needed to do each task is estimated based on size and productivity data or directly based on past experience.
Tasks are scheduled based on the team’s available hours.
If the overall plan appears not to satisfy management’s goals, the team may create some alternative proposals.
Overall plan
Available time
Estimate resources
Define tasks
Estimate size
Notes: <number>

## Slide 23: Meeting 5: Developing the Quality Plan
The team builds a quality plan for the product that shows how the team will achieve its product quality goal.
The team checks the quality plan against the goals and the overall plan to
  ensure that they are consistent
  check for needed adjustments
In the TSP, software quality during product development is measured by counting defects and normalizing by the appropriate size measure.
Quality plan
Quality goals
Defects injected
Defects removed
Notes: <number>

## Slide 24: Meeting 6: Building Detailed Next-phase Plans
The tasks for the next phase are allocated to the developers.
  The developers build their own work plans.
  The team balances the workload so that everyone completes their next-phase tasks at approximately the same time.
  The team merges the individual work plans to form a consolidated team plan.
This plan is used by the team to guide and track its work during the upcoming project phase.
Balanced
plan
Allocate tasks
Individual plans
Balance workload
Notes: <number>

## Slide 25: Meeting 7: Conducting a Risk Assessment
The team identifies and assesses the risks to its plan.
  Each risk is assessed for impact and likelihood.
  Mitigation plans are defined for high- and medium-priority risks.
Each risk is assigned to a team member for investigation and tracking.
Notes: <number>

## Slide 26: Meeting 8: Preparing the Management Presentation
The team prepares a presentation of the plan to management.
If the team’s plan does not meet management’s goals, the team includes alternative plans that either
  add more resources
  deliver a reduced-functionality version
  start small and follow later with a fully functioned version
Notes: <number>