## Slide 1: A Discipline for Software Engineering
Session 5 – Planning with a Model

## Slide 2: Document Markings
Copyright 2020 Carnegie Mellon University. All rights reserved. This material is based upon work funded and supported by the Department of Defense under Contract No. FA8721-05-C-0003 with Carnegie Mellon University for the operation of the Software Engineering Institute, a federally funded research and development center. Any opinions, findings and conclusions or recommendations expressed in this material are those of the author(s) and do not necessarily reflect the views of the United States Department of Defense. NO WARRANTY. THIS MATERIAL IS FURNISHED ON AN “AS-IS” BASIS WITH NO WARRANTIES OF ANY KIND, EITHER EXPRESSED OR IMPLIED, INCLUDING, BUT NOT LIMITED TO, WARRANTY OF FITNESS FOR PURPOSE OR MERCHANTABILITY, ANY WARRANTY WITH RESPECT TO FREEDOM FROM PATENT, TRADEMARK, OR COPYRIGHT INFRINGEMENT, OR THIRD PARTY INTELLECTUAL PROPERTY RIGHTS. [Distribution Statement A] This material has been approved for public release and unlimited distribution. The United States Government has Unlimited Rights in this material as defined by DFARS 252.227-7013.
The text and illustrations in this material are licensed by Carnegie Mellon University under a Creative Commons Attribution 4.0 International License.
The Creative Commons license does not extend to logos, trade marks, or service marks of Carnegie Mellon University.

## Slide 3: Problem: Estimating Size Before Development
Because product size is related to the development effort, if we know the size we can estimate the effort and schedule.
The problem is that we cannot directly measure size until the product is nearly complete.
Initially we have only requirements.
Unfortunately, most requirements
are not directly related to development effort
do not account for implementation variations such as programming language or reuse
are not easily (or automatically) countable
Notes: Design: still want to get away from thinking this is a design
Set the expectations for the detail
Decompose the problem into pieces that are recognizable

## Slide 4: Plan in Enough Detail to Be Useful
  If you do not understand what the product looks like, then you do not know enough to make an estimate.
  Good size estimates are detailed because that assures most needs are accounted for and the parts are small enough to understand.
  Early estimators usually cannot think in detail because requirements do not uniquely map to a product.
The basic issues are
conceptually mapping all requirements to the product
our limited capacity to visualize the detail
keeping track of all the parts
Notes: Decompose the problem until you have parts that you recognize
Setting up the idea of proxies

## Slide 5: Solution: Decompose the Solution
Decompose the problem to identify the implementable parts. User stories are one technique. We will use a Planning Model because we want to reason about the implementation.
The Planning Model is notional. It identifies pieces that could be used to construct the program, if they existed.
A Planning Model
  conceptually relates the functional requirements to product parts
  identifies the product elements that will produce the desired functionality
  decomposes and refines the solution into sufficient detail to identify recognizable parts
  records the parts so you do not forget anything
Notes: This example is usually best shown on flip charts or a white board. These slide are here as backup. So, if possible, cover this as a discussion with the class using the whiteboard/flip charts, and just skip over these slides.
Estimate
Decompose the problem
This may be different for individuals with different levels of experience
If the subject comes up in discussion, user stories are fine as far as they go, but they do not directly relate the solution to an implementation. Our planning model helps to think about what specifically will be changed.

## Slide 6: Size Estimating Overview Without Historical Data
Repeat until the product parts are the right size
Obtain potential
base code
Produce
Planning Model
Refine the
product into parts
Can you reuse a
base part?
Sum the estimated sizes
of the new and modified
parts
Estimate the
total added sizes
Repeat for all parts
Product Requirements
Size estimate
Yes
No
Estimate new part LOC
Do the parts resemble
parts you are familiar with?
Measure base total LOC, and estimate added and deleted LOC to modify the base part
All parts estimated?
Yes
No
Yes
No

## Slide 7: Example
Requirements
Produce a program to take records of data from a file
Store the data internally using a linked list
Compute the mean and standard deviation
Print the result to an output file

## Slide 8: Produce a Planning Model
Input Data
Linked List
Calc. Mean
Calc. SD
Print Result
Main
Notes: This example contains a file input, file output, linked list storage, and two cacuminal routines
The Linked List is estimated as a package, but could be further decomposed into specific items.
Describe the requirements for assignment 1
Discussion:
This is not a real design. It is a preliminary design that maps functionality to physical components. The planning model largely ignores many aspects, including non-functional attributes, details of the data flow or control flow, explicit algorithms or interfaces. It can consider reusable components, library packages, and so forth.

## Slide 9: Identify Base Parts to Modify or Reuse
Often, you begin with an existing program or parts.
Some parts need only small changes, such as
deleting unused calls or processing
modifying variable names, loop conditions, or file names
adding new calculations of function calls
For parts that you intend to modify,
measure the size
estimate the added, deleted, and modified lines directly
record your measures and estimates
Base Part | (B)ase size | (A)dded | (D)eleted | (M)odified
Main | 50 | 10 | 5 | 5
Linked list | 50 | 10 | 0 | 5
Notes: Most programs started out as Hello World.
You may have a linked list that you must alter to support this data record

## Slide 10: Estimating the New Parts
Base Program
Si
Added
Delete
Part | New Item | (B)ase Size | (A)dded | (D)eleted | (M)odified
Math package |  | 150 | 10 | 0 | 0
Math package | Calc SD | 0 | 20 | 0 | 0
Math package | Calc mean | 0 | 10 | 0 | 0
Data input |  | 0 | 50 | 0 | 0
Other parts may be all new or may include new items such as added methods.
Estimate the parts added to the base and new parts.
Notes: In this example, we will modify the math Package
We must modify the class interface and add two methods
We will add a new data input module.

## Slide 11: Completing the Estimate
Estimate the Total new program size (T). Start with the Base lines of code, then add all the Added lines of code, and finally subtract all the Deleted lines of code.
T = B + A – D
Calculate the Estimated new code by summing the Added and the Modified code from all base and new parts.
E = A + M
Notes: T = total